## Overview
SalesGenie AI – Day Team Project Schedule
AI Sales Assistant & Lead Intelligence Platform — SDLC Execution Plan
Project Start Date | 2026-07-15
Project End Date (Day 30) | 2026-08-25
Total Duration | 30 Days (incl. weekends as buffer/testing days)
How to use this workbook
1. Set the Project Start Date in cell C5 (yellow) — all schedule dates recalculate automatically.
2. 'Team Assignment' sheet — assign real names against each role.
3. '30-Day Schedule' sheet — day-by-day SDLC plan with owner and deliverable per day.
4. 'Module Task Breakdown' sheet — detailed task list per module mapped to owners with start/end dates.
5. 'Milestone Tracker' sheet — high-level 4-milestone view with evaluation criteria and sign-off status.
6. Update the 'Status' columns (dropdown: Not Started / In Progress / Completed / Blocked) as the team executes.
Team Size Assumption
6 members: Project Lead, Backend Developer, Frontend Developer, AI/ML Engineer, Database/DevOps Engineer, QA Engineer

## Team Assignment
Team Roles & Responsibilities
# | Role | Team Member (Name) | Primary Responsibility | Modules Owned | Tech Stack
1 | Project Lead / Scrum Master | Divya Bharathi I | Sprint planning, task allocation, client demo, risk tracking, evaluation sign-off | All modules (oversight) | Jira/Trello, Git, Docs
2 | Backend Developer | Divya Bharathi I | FastAPI endpoints, business logic, API security, RBAC, integration layer | Module 1, 3, 4, 5 (API layer) | FastAPI, Pydantic, JWT
3 | Database / DevOps Engineer | Guna Shekar Naidu Khandapu | PostgreSQL schema, migrations, indexing, Docker deployment, CI/CD, monitoring | Module 1 (DB), Module 6 (deployment) | PostgreSQL, SQLAlchemy, Docker
4 | AI/ML Engineer | Jagadeesh | LangGraph agents, LLM prompt design, lead scoring model, outreach generation, summarization | Module 2, 3, 4, 5 (AI layer) | LangGraph, Groq/OpenAI API
5 | Frontend Developer | Gopika Rajendiran | Streamlit UI, dashboard, theming/CSS, session state, API integration on client side | Module 1 UI, Module 6 (Dashboard) | Streamlit, Plotly/Altair, CSS
6 | QA / Test Engineer | Gilagalla Karthik | Test case design, functional & integration testing, UAT, accuracy validation (scoring, insights) | All modules (testing) | Pytest, Postman, Manual QA

## 30-Day Schedule
30-Day Day-wise SDLC Execution Schedule
Dates auto-calculate from Overview!C5 (Project Start Date)
Day | Date | SDLC Phase | Milestone | Module Focus | Key Task | Owner (Role) | Deliverable | Status
1 | 2026-07-15 | Planning & Requirement Analysis | Kickoff | All Modules | Requirement gathering, finalize scope, review architecture & DB schema diagrams | Project Lead + Full Team | Signed-off SRS document | Completed
2 | 2026-07-16 | Planning & Requirement Analysis | Kickoff | All Modules | Define API contracts (endpoints list), tech stack finalization, repo & branching setup | Project Lead + Backend Dev | Git repo, API contract doc | Completed
3 | 2026-07-17 | Planning & Requirement Analysis | Kickoff | All Modules | Sprint planning for Milestone 1; task breakdown & estimation in tracker | Project Lead | Sprint 1 backlog | Completed
4 | 2026-07-20 | System & Database Design | Milestone 1 Prep | Module 1 | Design ER diagram & finalize PostgreSQL schema (Leads, Users, CRM_Sync_Logs) | Database/DevOps Engineer | Finalized DB schema + migration scripts | Completed
5 | 2026-07-21 | System & Database Design | Milestone 1 Prep | Module 1/6 | Design Streamlit wireframes (Leads, Outreach, Conversations, Dashboard tabs) | Frontend Developer | UI wireframes / mockups | Completed
6 | 2026-07-22 | System & Database Design | Milestone 1 Prep | Module 2 | Design LangGraph agent architecture (Research, Qualification, Outreach, CRM agents) | AI/ML Engineer | Agent architecture diagram | Completed
7 | 2026-07-23 | Development | Milestone 1 | Module 1 | Implement Lead/Prospect DB models, CRUD APIs (create/edit/search prospects) | Backend Developer | Prospect CRUD API (FastAPI) | Completed
8 | 2026-07-24 | Development | Milestone 1 | Module 1 | Build lead import (CSV upload, manual entry) with duplicate detection | Backend Developer | Lead import module | Completed
9 | 2026-07-27 | Development | Milestone 1 | Module 1 | Build Streamlit 'Leads' tab: prospect search list + detail panel | Frontend Developer | Leads UI screen | Completed
10 | 2026-07-28 | Development | Milestone 1 | Module 2 | Implement company profile analysis logic (industry, size, tech stack ingestion) | AI/ML Engineer | Company profile analysis service | Completed
11 | 2026-07-29 | Development | Milestone 1 | Module 2 | Build AI qualification scoring prompt + Lead Intelligence card generation | AI/ML Engineer | Qualification score engine | Completed
12 | 2026-07-30 | Development | Milestone 1 | Module 2 | Integrate Lead Intelligence output into Leads UI (score badge, insights panel) | Frontend Developer + AI/ML Engineer | Lead Intelligence UI integration | Completed
13 | 2026-07-31 | Testing & QA | Milestone 1 | Module 1/2 | Unit test lead CRUD + review qualification score accuracy on sample data | QA Engineer | Milestone 1 test report | Completed
14 | 2026-08-03 | Testing & QA | Milestone 1 | Module 1/2 | Milestone 1 review: ≥95% prospect records manageable, insights accuracy check; sign-off | Project Lead + QA | Milestone 1 sign-off (Day 14 checkpoint) | Completed
15 | 2026-08-04 | Development | Milestone 2 | Module 3 | Build AI email/outreach generation service (prompt templates per industry) | AI/ML Engineer | Outreach generation API | Completed
16 | 2026-08-05 | Development | Milestone 2 | Module 3 | Build Streamlit 'Outreach' tab: AI Email Generator UI with edit-before-send | Frontend Developer | Outreach UI screen | Completed
17 | 2026-08-06 | Development | Milestone 2 | Module 4 | Implement lead scoring & conversion probability model (rules/ML features) | AI/ML Engineer + Backend Developer | Lead scoring engine | Completed
18 | 2026-08-07 | Development | Milestone 2 | Module 4 | Build recommendation engine: follow-up timing, channel mix, content strategy | AI/ML Engineer | Recommendation engine service | Completed
19 | 2026-08-10 | Development | Milestone 2 | Module 4 | Integrate Lead Score + Outreach Strategy cards into Outreach UI | Frontend Developer | Outreach Strategy UI panel | Completed
20 | 2026-08-11 | Testing & QA | Milestone 2 | Module 3/4 | Validate lead scoring accuracy (target ≥85%), test outreach across 3+ industries; sign-off | QA Engineer + Project Lead | Milestone 2 sign-off (Day 20 checkpoint) | Completed
21 | 2026-08-12 | Development | Milestone 3 | Module 5 | Build FastAPI endpoints for CRM integration (Salesforce/HubSpot schema mapping) | Backend Developer | CRM integration API | Completed
22 | 2026-08-13 | Development | Milestone 3 | Module 5 | Implement CRM sync logic (contacts, activities, deal stages) + sync logs | Backend Developer + DevOps Engineer | CRM sync service | Completed
23 | 2026-08-14 | Development | Milestone 3 | Module 5 | Build meeting/call summarization (key points + action item extraction) via LLM | AI/ML Engineer | Conversation summarization service | Completed
24 | 2026-08-17 | Development | Milestone 3 | Module 5 | Build Streamlit 'Conversations' tab: CRM Sync Status + Meeting Summary + Activity feed | Frontend Developer | Conversations UI screen | Completed
25 | 2026-08-18 | Testing & QA | Milestone 3 | Module 5 | Test CRM sync across workflows, validate summarization output quality; sign-off | QA Engineer + Project Lead | Milestone 3 sign-off (Day 25 checkpoint) | Completed
26 | 2026-08-19 | Development | Milestone 4 | Module 6 | Build Sales Analytics Dashboard (conversion rate, pipeline value, sales cycle KPIs) | Frontend Developer + Backend Developer | Dashboard UI + analytics API | Completed
27 | 2026-08-20 | Development | Milestone 4 | Module 6 | Implement Kanban-style pipeline view + automated follow-up recommendations panel | Frontend Developer + AI/ML Engineer | Pipeline view + follow-up panel | Completed
28 | 2026-08-21 | Integration | Milestone 4 | All Modules | End-to-end integration of all 6 modules; performance tuning (<5 sec response target) | Full Team | Integrated end-to-end build | Completed
29 | 2026-08-24 | Testing & QA | Milestone 4 | All Modules | Full regression testing, UAT with sample users, capture satisfaction score (target ≥85%) | QA Engineer + Project Lead | UAT report + test sign-off | Completed
30 | 2026-08-25 | Deployment & Closure | Milestone 4 | All Modules | Deploy to production/staging (Docker), final demo, documentation handover, retrospective | Full Team | Deployed app + final demo + project closure doc | Completed

## Module Task Breakdown
Module-wise Task Breakdown with Start/End Day & Owner
Module | Task | Owner (Role) | Start Day | End Day | Start Date | End Date | Duration (Days) | Deliverable | Status
Module 1: Lead Management & Prospect Database | Design DB schema (Leads, Users, CRM_Sync_Logs) | Database/DevOps Engineer | 4 | 4 | 2026-07-20 | 2026-07-20 | 1 | Finalized schema + migrations | Completed
Module 1: Lead Management & Prospect Database | Build prospect CRUD APIs | Backend Developer | 7 | 8 | 2026-07-23 | 2026-07-24 | 2 | FastAPI CRUD endpoints | Completed
Module 1: Lead Management & Prospect Database | Build lead import (CSV/manual) with de-duplication | Backend Developer | 8 | 8 | 2026-07-24 | 2026-07-24 | 1 | Lead import module | Completed
Module 1: Lead Management & Prospect Database | Build Leads UI (search list + detail panel) | Frontend Developer | 9 | 10 | 2026-07-27 | 2026-07-28 | 2 | Leads tab (Streamlit) | Completed
Module 2: Lead Intelligence & Company Analysis | Design LangGraph agent architecture | AI/ML Engineer | 6 | 6 | 2026-07-22 | 2026-07-22 | 1 | Agent architecture diagram | Completed
Module 2: Lead Intelligence & Company Analysis | Build company profile analysis service | AI/ML Engineer | 10 | 11 | 2026-07-28 | 2026-07-29 | 2 | Company analysis service | Completed
Module 2: Lead Intelligence & Company Analysis | Build qualification scoring engine | AI/ML Engineer | 11 | 12 | 2026-07-29 | 2026-07-30 | 2 | Qualification score API | Completed
Module 2: Lead Intelligence & Company Analysis | Integrate insights into Leads UI | Frontend Developer + AI/ML Engineer | 12 | 12 | 2026-07-30 | 2026-07-30 | 1 | Lead Intelligence panel | Completed
Module 3: AI Outreach Generation | Build outreach/email generation service | AI/ML Engineer | 15 | 16 | 2026-08-04 | 2026-08-05 | 2 | Outreach generation API | Completed
Module 3: AI Outreach Generation | Build Outreach UI (AI Email Generator) | Frontend Developer | 16 | 17 | 2026-08-05 | 2026-08-06 | 2 | Outreach tab (Streamlit) | Completed
Module 4: Lead Scoring & Recommendation Engine | Build lead scoring & conversion probability model | AI/ML Engineer + Backend Developer | 17 | 18 | 2026-08-06 | 2026-08-07 | 2 | Lead scoring API | Completed
Module 4: Lead Scoring & Recommendation Engine | Build next-best-action recommendation engine | AI/ML Engineer | 18 | 18 | 2026-08-07 | 2026-08-07 | 1 | Recommendation service | Completed
Module 4: Lead Scoring & Recommendation Engine | Integrate scoring & strategy into Outreach UI | Frontend Developer | 19 | 19 | 2026-08-10 | 2026-08-10 | 1 | Outreach Strategy panel | Completed
Module 5: Conversation Intelligence & CRM Integration | Build CRM integration APIs (Salesforce/HubSpot mapping) | Backend Developer | 21 | 22 | 2026-08-12 | 2026-08-13 | 2 | CRM integration API | Completed
Module 5: Conversation Intelligence & CRM Integration | Implement CRM sync logic + sync logs | Backend Developer + DevOps Engineer | 22 | 23 | 2026-08-13 | 2026-08-14 | 2 | CRM sync service | Completed
Module 5: Conversation Intelligence & CRM Integration | Build meeting/call summarization + action item extraction | AI/ML Engineer | 23 | 24 | 2026-08-14 | 2026-08-17 | 2 | Summarization service | Completed
Module 5: Conversation Intelligence & CRM Integration | Build Conversations UI (sync status, summary, activity feed) | Frontend Developer | 24 | 24 | 2026-08-17 | 2026-08-17 | 1 | Conversations tab (Streamlit) | Completed
Module 6: Dashboard & Sales Analytics | Build analytics API (conversion rate, pipeline value, KPIs) | Backend Developer | 26 | 27 | 2026-08-19 | 2026-08-20 | 2 | Analytics API | Completed
Module 6: Dashboard & Sales Analytics | Build dashboard UI + pipeline Kanban view | Frontend Developer | 26 | 27 | 2026-08-19 | 2026-08-20 | 2 | Dashboard tab (Streamlit) | Completed
Module 6: Dashboard & Sales Analytics | Build automated follow-up recommendation panel | AI/ML Engineer + Frontend Developer | 27 | 27 | 2026-08-20 | 2026-08-20 | 1 | Follow-up panel | Completed
Cross-Module | End-to-end integration & performance tuning | Full Team | 28 | 28 | 2026-08-21 | 2026-08-21 | 1 | Integrated build | Completed
Cross-Module | Full regression testing & UAT | QA Engineer | 29 | 29 | 2026-08-24 | 2026-08-24 | 1 | UAT + test report | Completed
Cross-Module | Deployment, documentation & final demo | Full Team | 30 | 30 | 2026-08-25 | 2026-08-25 | 1 | Deployed app + docs | Completed

## Milestone Tracker
Milestone Tracker & Evaluation Criteria
Milestone | Day Range | Start Date | End Date | Modules Covered | Evaluation Criteria | Sign-off Status
Milestone 1 | Day 1-14 | 2026-07-15 | 2026-07-28 | Module 1 (Lead Management) + Module 2 (Lead Intelligence) | Manage/analyze ≥95% of prospect records; generate accurate company insights & lead intelligence | Signed Off
Milestone 2 | Day 15-20 | 2026-07-29 | 2026-08-03 | Module 3 (AI Outreach) + Module 4 (Lead Scoring) | Lead scoring accuracy ≥85%; personalized outreach content generated for multiple industries | Signed Off
Milestone 3 | Day 21-25 | 2026-08-04 | 2026-08-08 | Module 5 (CRM Integration & Conversation Intelligence) | CRM integration functions correctly across supported workflows; sales conversation summaries generated successfully | Signed Off
Milestone 4 | Day 26-30 | 2026-08-09 | 2026-08-13 | Module 6 (Dashboard & Analytics) + Full Integration | Dashboard fully operational; end-to-end workflow functional; response time <5 sec; user satisfaction ≥85% | Signed Off